## Priority Test (hidden)
S. No | Name of Test | Requirement | Sample Requirement | Mandays
1 | Spark | Test the meter for 4 days | 3 | 1
2 | Jammer |  | 3 | 1
3 | Magnet |  | 3 | 5
4 | NM |  | 2 | 3
5 | ND |  |  | 3
6 | Surge |  | 3 | 2
7 | Impulse |  | 3 | 1
8 | Battery Consumption |  | 2 | 3
9 | RE |  | 3 | 2
10 | CE |  |  | 0.5
11 | RS |  | 3 | 3
12 | ESD |  |  | 1
13 | EFT |  |  | 1.5
CS

## Abbreviation of Test Plan_HW
Name of Project |  | Test Level | Hardware Validation Test Summary
S. No. | Group of Test | 1. Critical 2. Hard to pass 3. Others |  | Required | Metering Mode |  | Current Direction |  | Measurement Element |  |  | Payment Mode |  | kVAh Calculation |  | Optical Communication |  | Remote Comm. |  | Comm. Technology |  |  | Man Days Required for the test | Final Man Days | Easy to Pass | Hard to Pass | Trouble sum Test
|  |  | FALSE | Not Required | Import Only | Import- Export | Forward | Reverse | Phase Only | Neutral Only | Combined Element | Prepaid and Zero bal. when BL Blinking | Prepaid balance is above 500 INR and BL not blinking | Lag Only | Lag+ Lead | When Contineously ON | When idle mode | When Contineously ON | When idle mode | NAN | WAN | IMG
A | Metrology and Electrical Requirement | 2 | FALSE
1 | Limits of Error (150% Imax to 1% Ib) | 2 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 9
2 | Starting Current | 2 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
3 | No-Load | 2 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
4 | Voltage Variation | 2 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
5 | Frequency Variation | 2 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
6 | 3rd Harmonics | 2 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
7 | 5th Harmonics | 2 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
8 | Repeatability of Error | 2 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
9 | Dial Test | 2 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 | Constant Test | 2 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
11 | Dial test With MD | 2 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
12 | Power Consumption | 2 | TRUE |  | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 1
13 | Self Heating test | 2 | TRUE |  | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 1
14 | Voltage Dips and Interupption | 2 | TRUE |  | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 0.5
15 | DC Immunity Test | 2 | TRUE |  | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1.5
16 | Operation of accessories | 2 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0.5
B | Magnet Test |  | FALSE
1 | 0.5T Permanent Magnet | 1 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
2 | 10mT±5% AC Magnet | 1 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
3 | 0.27T±5% DC MAgnet | 1 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
4 | 0.2T±5% DC Magnet | 1 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2.5
5 | 67mT±5% DC Magnet | 1 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
C | Non Standard Tests |  | FALSE
1 | 35kv Test | 1 | TRUE |  | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | 1
2 | Jammer Test | 1 | TRUE |  | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | 1
3 | 650V Test for 6 Hrs | 2 | TRUE |  | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | 1
4 | 150% Imax for 6 Hrs | 1 | TRUE |  | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 1
5 | Drop Test | 3 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 1
6 | Free Fall Test | 3 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
7 | Rolling Test | 3 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
8 | Halt Testing | 2 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 8
9 | Push Button Operation | 1 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 | Cable Pull Force | 3 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
11 | SIM Card Operation | 2 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0.5
12 | Modem Plug-in Plug Out Test | 2 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0.5
13 | Display viewing angle test | 2 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
14 | Transport Test | 3 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
15 | Internal Screw Torque and tightness test | 3 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0.5
16 | Connection screw torque and tightness test | 3 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0.5
17 | Waltky-Talky test | 3 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 | Mobile Influence test | 3 | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | 1
19 | LCD temperature test | 1 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 6
20 | Meter Display validation – Legibility and Readability | 3 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2
21 | Par Lamp Test with resistive load bulb | 3 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
22 | Light intensity test | 3 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
23 | Audible Noise Test | 3 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
24 | Graceful failure test | 3 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
25 | RF Range Test | 1 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 5
26 | Faraday Cage Test | 2 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
27 | Tamper Through Terminal using 0.3 mm Wire | 3 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
28 | Intrruption test with timer | 1 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 6
29 | Salt Spray Test | 3 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
30 | Thermal Cycle Test | 3 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
31 | Test of UV Effect | 3 | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
32 | Battery Consumption Test | 1 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1.5
D | Insulation Test |  | FALSE
1 | High Voltage Test | 2 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 0.5
2 | Insulation Resistance | 2 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 0.5
3 | Impulse Voltage Test | 1 | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 1
E | Climatic Related Test |  | TRUE
1 | Influence of Heating |  | TRUE |  | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
2 | Influence of ambient Temperature (Temco) |  | TRUE |  | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2
3 | Dry Heat Test |  | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 4
4 | Cold Test |  | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 4
5 | Damp Heat Test |  | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 7
F | EMI/EMC Test |  | TRUE
1 | Radiated Emission Test |  | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 1.5
2 | Conducted Emission Test |  | TRUE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 0.5
3 | Fast Transient Burst Test |  | TRUE |  | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 1
4 | ESD Test |  | TRUE |  | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 1
5 | RS Test |  | TRUE |  | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 3
6 | Surge Immunity Test |  | TRUE |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 2
G | Mechanical Tests |  | TRUE
1 | Vibration Test |  | TRUE |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 1
2 | Shock Test |  | TRUE |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 1
3 | Spring Hammer Test |  | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4 | IP Test |  | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 | Glow Wire |  | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[23 empty] | 94.5 | 0
[19 empty] | Minimum reqired working days for Hardware |  |  |  | 25 Days
[19 empty] | Minimum reqired working days for Comms Testing |  |  |  | 10 Days
[19 empty] | Minimum reqired working days for Firmware Testing |  |  |  | 13 Days
Project testing Start Date
Project Expected testing End Date

## Abbreviation of Test Plan_FW
SN | Group of Test | Time Estimate in day
1 | Default Paramter After Factory Reset | 1
2 | Optical Communication For All Association(DLMS)
3 | Battery Consumption + Self Diagnostic
4 | Production Tool
5 | Instantaneous + Energy increment (In Lag only & Lag + Lead) | 1.5
6 | NIC Removal & NIC swapping | 1
7 | Battery mode communication (5 times) compare data with power on - All parameter reading | 1
8 | Bitmask for load survey (TAP-via Pubsub) RF
9 | Chattering
10 | Power cycle Push 10 times on HES(WAN & NAN)
11 | Rollover For All Profile | 0.25
12 | All Profile (compartment size) | 0.25
13 | Billing, TOD and MD (In Lag only & Lag + Lead) | 5
14 | Start up Voltage Test (WAN & NAN) | 1
15 | NM Enable (From DLMS & TAP)
16 | Name plate | 1.5
17 | 4G Fallback 2G
18 | Transaction (GPRS)
19 | Internal version (HES, DLMS)
20 | Time set w/o Log (HES , DLMS)
21 | Relase Note ( validation ) | 0.5
22 | Display | 2
23 | Tamper + Actual tamper | 6
24 | Load limit | 1.5
25 | Block load , Daily load (In Lag only & Lag + Lead) | 5
26 | Periodic Push / Event Push(DLMS) | 2
27 | Read all profile from long Run using HES & Gurux | 1
28 | Firmware Upgrade | 1.5
29 | Tap Commands via HES | 4
30 | RTC Effect | 1
31 | Module LED | 1
32 | Local Relay Connection (LRC) | 2
33 | TOD Push via HES | 1
34 | RTC Logic(Interruption) | 1
35 | AC Chopping, DC Chopping/Injection | 4
36 | Old BUG verification | 3
37 | Interruption Test | 1
38 | Smoke Test | 1
| Total Days | 51

## Abbreviation of TP_Module HW
4G Module H/W Testing Timing
Test Case ID | Test Name | Test Time
TC-01 | Signal Strength Test | 15–20 min
TC-02 | Network Registration Test | 5 min
TC-03 | Data Communication Test | 20–30 min
TC-04 | Voltage Ckt- Power Consumption Test (Just ON Case) | 10–15 min
TC-05 | Voltage Ckt- Power Consumption Test (Just OFF Case) | 10–15 min
TC-06 | Voltage Ckt- Power Consumption Test (Network Latchup) | 15–20 min
TC-07 | Voltage Ckt- Power Consumption Test ( Low Network ) | 20–30 min
TC-08 | Voltage Ckt- Power Consumption Test ( Continuous communication) | 15–20 min
TC-09 | Voltage Ckt- Power Consumption Test ( faraday Case ) | 15–20 min
TC-10 | Multiple Device Interference | 15–20 min
TC-11 | RF Jammer Test | 15–20 min
TC-12 | Radiated Spark Test | 10–15 min
TC-13 | Radiated & Conducted Spark Test (35kV) | 10–15 min
TC-14 | Cold Test (-40°C) | 45–75 min
TC-15 | Dry Heat Test (70°C) | 45–75 min
TC-16 | Damp Heat Cycle Test | 75–90 min
TC-17 | 85°C / 85% RH Test | 75–90 min
TC-18 | Chattering Test | 15–20 min
TC-19 | Power ON/OFF Test | 15–20 min
TC-20 | Vibration Test (2G/3G) | 25–35 min
TC-21 | Shock Test (40G) | 15–20 min
TC-22 | Drop Test | 15–20 min
TC-23 | Conducted Emission (CE) Test | 25–35 min
TC-24 | Radiated Emission (RE) Test | 25–35 min
TC-25 | Radiated Immunity (RS) Test | 25–35 min
TC-26 | EFT Test | 15–20 min
TC-27 | ESD Test | 15–20 min
TC-28 | Surge Test | 15–20 min
TC-29 | Latency Test | 15–20 min
TC-30 | Packet Loss Test | 20–30 min
TC-31 | Field Range Test | 30–45 min
TC-32 | Antenna Performance Test | 20–30 min
TC-33 | SIM Functionality Test | 10–15 min
TC-34 | Network Handover Test | 20–30 min
TC-35 | Reconnection Test | 15–20 min
TC-36 | Long Duration Stability Test | 48–72 hrs
TC-37 | Throughput Test | 25–35 min
TC-38 | DNS Resolution Test | 10–15 min
TC-39 | TCP Port Test | 10–15 min
TC-40 | APN Configuration Test | 10–15 min
TC-41 | SIM Swap Test | 15–20 min
TC-42 | Cold Start Test | 10–15 min
TC-43 | Signal Recovery Test | 15–20 min
TC-44 | Server Failover Test | 20–30 min
TC-45 | Data Integrity Test | 15–20 min
TC-46 | Security Test | 20–30 min
TC-47 | Time Sync Test | 10–15 min
TC-48 | Jitter Test | 15–20 min
TC-49 | Socket Stability Test | 45–75 min
TC-50 | Data Retry Test | 15–20 min
TC-51 | Buffer Overflow Test | 20–30 min
TC-52 | Memory Leak Test | 3–5 hrs
TC-53 | CPU Load Test | 20–30 min
TC-54 | Power Failure Test | 15–20 min
TC-55 | RTC Backup Test | 15–20 min
TC-56 | Event Logging Test | 15–20 min
TC-57 | Watchdog Test | 15–20 min
TC-58 | Roaming Test | 30–45 min
TC-59 | Earth Fault Test | 15–20 min
TC-60 | Accessories Operation Test | 15–20 min
TC-61 | Temco Test | 25–35 min
TC-62 | Heating Test | 25–35 min
TC-63 | Limits of Error (Balanced) | 15–20 min
TC-64 | Limits of Error (Unbalanced) | 15–20 min
TC-65 | Initial Start-Up Test | 10–15 min
TC-66 | Starting Current Test | 10–15 min
TC-67 | Voltage Variation Test | 15–20 min
TC-68 | Frequency Variation Test | 15–20 min
TC-69 | Harmonics Test | 15–20 min
TC-70 | Reverse Phase Sequence Test | 10–15 min
TC-71 | Voltage Unbalance Test | 15–20 min
TC-72 | AC Magnet Test | 15–20 min
TC-73 | DC Magnet Test | 15–20 min
TC-74 | Conductive Spark Test | 10–15 min
TC-75 | Module Plug In/Out Test | 15–20 min
TC-76 | SIM In/Out Test | 15–20 min
TC-77 | SIM Deactivation Test | 10–15 min
TC-78 | Dual SIM Test | 15–20 min
TC-79 | Drop Test (Field) | 10–15 min
TC-80 | Interruption Test | 10–15 min
TC-81 | Magnet Tamper Test | 10–15 min
TC-82 | Relay Test | 10–15 min
TC-83 | Continuous Data Test | 25–30 min
TC-84 | Firmware Update Test | 30–45 min
TC-85 | FW Update (Power OFF) | 20–30 min
TC-86 | FW Update (Interrupt) | 20–30 min
TC-87 | Long Duration Run | 60–80 hrs
TC-88 | Enclosure Test | 15–20 min
TC-89 | Network Switch Test | 15–20 min
TC-90 | Weak Signal Test | 20–30 min
TC-91 | Long Magnet Test | 45 min
TC-92 | Flickering Magnet Test | 15–20 min
TC-93 | Magnet Enclosure Test | 15–20 min
TC-94 | SIM Switch During Comm | 15–20 min
TC-95 | Low Voltage Test | 15–20 min
TC-96 | RTC Drift Test | 24–30 hrs
TC-97 | Sunlight Exposure Test | 45 min
TC-98 | Multi-Network Interference | 20–30 min
TC-99 | Invalid Command Spam Test | 15–20 min
| Total Hours | 145
| Total Days | 18.125

## Abbreviation of TP_CommsTesting
4G Module F/W Testing Timing
Sr. No. | Master List / Module Name | Master List | Test Time
1 | Provisioning Test | PROV_XXX | 0.5
2 | SIM functionality | SIM_FN_XXX | 9
3 | Data Push Test | PUSH_XXX | 9
4 | Data Pull Test | PULL_XXX | 4.5
5 | Meter Profile Read | PR_XXX | 4.5
6 | Network Validation | NET_VD_XXX | 9
8 | Module Swapping | MOD_SWP_XXX | 12
7 | Firmware Upgrade | FW_UPD_XXX | 25
9 | Module Stress Test | MOD_STR_XXX | 1.5
10 | Power Cycle Test | POW_CYC_XXX | 1.5
11 | Resilience Test | RESC_XXX | 2
12 | Chattering Test | CH_XXX | 2
13 | YAT Test | YAT_XXX | 3
14 | IMG Reset | IMG_RESET_XXX | 0.5
15 | Black Hole | IMG_FAIL_XXX | 2
16 | RTC sync | RTC_SYNC_XXX | 0.5
17 | RSSI | IMG_RSSI_XXX | 0.5
|  | Total Hours | 86.5
|  | Total Days | 10.1765